## Sheet1
TOY FAIR 2022 QUICK REFERENCE DEADLINE CHECKLIST
| DEADLINE DATE | Notes
FOR ALL EXHIBITORS
Online Exhibitor Listing (including supplementary brands) | 20th October and ongoing | After this date entries will still be published subject to a delay (copy approval)
Classified Products List- categories that your products fall into | 20th October and ongoing
MANDATORY Exhibitor Risk Assessment and Health & Safety declaration (for show open period) | 4th November | ALL Exhibitors need to complete this documention to be permitted access on site
Registering Stand Staff | 6th Jan (badges posted to UK Exhibitors only) | Any stand staff registered after this date will receive e-badges to scan on site
MANDATORY FOR CONTRACTORS of ALL Self-Build Stands
Risk Assessment/Method Statement/CPP to toyfair@abraxys.com | 4th November
DRAFT stand plan designs to toyfair@abraxys.com | 4th November
FINAL stand plan designs to toyfair@abraxys.com | 6th December
OPTIONAL EXTRAS (NB: Any orders after these deadline dates may not be possible and may be subject to surcharges)
Stand Security- G4S | 13th December
Rigging- Outback | 7th January 2022
IT & Communications- E-Force | 21st Dec 2021, any bookings past this date will be charged the Late Rate
Graphics-GES | TBC
Electrics & Lighting- GES | TBC
Shell Scheme Extras- GES | TBC
Furniture-GES | TBC
Logistics- Agility | 4th January 2022
Catering- Host Olympia | Book and pay by 14th January 2020 for early booking discount (5% surcharge thereafter)
Compressed Air, Water and Waste- ATD | 23rd December early booking deadline
Show Offers | 6th January 2022
Visitor Scanners- Reftech | 6th January 2022 early bird rates, 15th January 2022 for standard rates
AV- Aztec | 11th Jan 2022 for 20% discount, normal rates after this date
Furniture- Xpect Furniture | TBC
Booking in vehicles for (un)loading | Ongoing
Sponsorship Opportunities- Toy Fair team | Ongoing
Stand Cleaning- Olympia Facilities Department | Ongoing
Accommodation/Travel- Event Express | Ongoing
Photography | Ongoing
Temp Staff- BOND associates | Ongoing
Temp staff- Smooth | Ongoing